## Sheet1
PRODUCT BACKLOG
ID | As a… | I want to be able | So that… | Priority | Sprint | Status
1 | Computer Science Student | Search for words that are widely used in IT field, mostly CS terminologies | Better know and understand what are their meaning in a technical context | Must | 1 | Done
2 | Computer Science Professor | Search for words which not only belong to Computer Science but any word that I read and don’t know the meaning | Find the relevant meaning of the word I am searching for | Must | 1 | Done
3 | English Professor | Search for the words that are mostly used in poems | Better translate words for my students in poems context | Could | 2 | Done
4 | Student | Dictionary to be very user friendly and easy to use | Search for words easily | Must | 1 | Done
5 | Student | Dictionary to be fast. It should be able to search for the words in a split second | Search for words without wasting my time | Must | 1 | Done
6 | Student | Dictionary to not have advertisement. They can be very distractive and annoying. | Search for words without wasting my time | Must | 1 | Done
7 | Student | Dictionary to have millions of words | Search for any kind of word I need the meaning for | Could | 2 | Done
8 | Student | Dictionary to be coded professionally without any bugs | Search for words and the dictionary does not crash and give error | Must | 1 | Done
9 | Student | Dictionary to translate to English to Dari – Dari to English | Search for words in English and know their meaning in my native language for better understanding of the language | Should | 2 | Done
10 | Student | Dictionary to translate to display the synonyms, antonyms, and examples for the searched word. | Better understand and use that word when speaking in English. | Could | 2 | Done