## Sheet1
No | User Stories |  |  | Tasks | Day - 1 | Day - 2 | Day - 3 | Day - 4 | Day - 5 | Day - 6 | Day - 7 | Day - 8 | Day - 8 | Day - 9 | Day - 10 | Day - 11 | Day - 12 | Day - 13 | Day - 14 | Day - 15 | Day - 16 | Day - 17 | Day - 18 | Day - 19 | Day - 20 | Day - 21 | Day - 22 | Day - 23 | Day - 24 | Day - 25 | Day - 25 | Day - 26 | Day - 27 | Day - 28 | Day - 29 | Day - 30
1 | As a | I want to be able | So that… | Code the Dictionary | 2hr | 2hr | 2hr | Friday | 1hr | 0hr | 2hr | 1hr | 1hr | 1hr | Friday | 1hr | Midterm Exam Week | [7 empty] | 0hr | 0hr | 0hr | 0hr | 2hr | Friday | 2hr | 3hr | 0hr | 0hr | 3hr | 4hr
| Computer Science Student | Search for words that are widely used in IT field, mostly CS terminologies | Better know and understand what are their meaning in a technical context
| Computer Science Professor | Search for words which not only belong to Computer Science but any word that I read and don’t know the meaning | Find the relevant meaning of the word I am searching for
| English Professor | Search for the words that are mostly used in poems | Better translate words for my students in poems context | Design the UI | 2hr | 2hr | 2hr |  | 1hr | 0hr | 2hr | 1hr | 1hr | 1hr |  | 1hr | [8 empty] | 0hr | 0hr | 0hr | 0hr | 2hr |  | 2hr | 3hr | 0hr | 0hr | 3hr | 4hr
| Student | Dictionary to be very user friendly and easy to use | Search for words easily
| Student | Dictionary to be fast. It should be able to search for the words in a split second | Search for words without wasting my time | Connectivity of Code with UI | 1hr | 1hr | 1hr |  | 1hr | 0hr | 1hr | 1hr | 1hr | 1hr |  | 1hr | [8 empty] | 0hr | 0hr | 0hr | 0hr | 1hr |  | 1hr | 2hr | 0hr | 0hr | 2hr | 2hr
| Student | Dictionary to not have advertisement. They can be very distractive and annoying. | Search for words without wasting my time
| Student | Dictionary to have millions of words | Search for any kind of word I need the meaning for | Write the test plan | 1hr | 1hr | 1hr |  | 1hr | 0hr | 1hr | 1hr | 1hr | 1hr |  | 1hr | [8 empty] | 0hr | 0hr | 0hr | 0hr | 1hr |  | 1hr | 1hr | 0hr | 0hr | 1hr | 1hr
| Student | Dictionary to be coded professionally without any bugs | Search for words and the dictionary does not crash and give error
| Student | Dictionary to translate to English to Dari – Dari to English | Search for words in English and know their meaning in my native language for better understanding of the language | Automate Tests | 1hr | 1hr | 1hr |  | 30mins | 0hr | 1hr | 30mins | 30mins | 30mins |  | 30mins | [8 empty] | 0hr | 0hr | 0hr | 0hr | 1hr |  | 1hr | 1hr | 0hr | 0hr | 1hr | 2hr
| Student | Dictionary to translate to display the synonyms, antonyms, and examples for the searched word. | Better understand and use that word when speaking in English.
The sprint backlog is created by the scrum master. But, during the Scrum sprint, development team members are expected to update the sprint backlog as new information is available, but minimally once per day. Many teams will do this during the daily scrum.